## Dashboard
UNIFIED SERVICE SCHEDULER — DELIVERY DASHBOARD
PLANNED HOURS |  |  | COMPLETED HOURS |  | PROGRESS
28 |  |  | 0 |  | 0%
WORK PACKAGE SUMMARY
WBS | Work Package | Hours | Outcome | Status | Task Count | Hours
1.0 | Requirement Analysis & System Design | 4 | Design baseline approved | Not Started | 40 | 28
2.0 | Project Setup & Data Model | 4 | Reproducible application and seeded database | In Progress | 0 | 0
3.0 | Availability Core | 4 | Availability endpoint and reusable rules | Blocked | 0 | 0
4.0 | Appointment & Concurrency Core | 4 | Atomic confirmed appointment | Done | 0 | 0
5.0 | Reliability & Observability | 4 | Retry safety and operational signals
6.0 | Tests, Contract & CI | 4 | Verified behavior and executable client stub
7.0 | Documentation & Submission | 4 | Complete submission package
USAGE: update Status in Task Backlog; dashboard formulas update automatically. Filter by category, priority or dependency during daily review.

## WBS
WBS | Work Package | Planned Hours | Primary Outcome
1.0 | Requirement Analysis & System Design | 4 | Design baseline approved
2.0 | Project Setup & Data Model | 4 | Reproducible application and seeded database
3.0 | Availability Core | 4 | Availability endpoint and reusable rules
4.0 | Appointment & Concurrency Core | 4 | Atomic confirmed appointment
5.0 | Reliability & Observability | 4 | Retry safety and operational signals
6.0 | Tests, Contract & CI | 4 | Verified behavior and executable client stub
7.0 | Documentation & Submission | 4 | Complete submission package
Summary | Formula
Total planned hours | 28
Work packages | 7

## Task Backlog
Task ID | WBS | Task | Description | Category | Hours | Priority | Status | Dependencies | Definition of Done
TASK-001 | 1.1 | Requirement mapping | Rewrite the challenge into testable backend requirements and map each requirement to evidence. | Design | 0.5 | Must | Not Started | None | Requirement map reviewed; each acceptance criterion links to an endpoint and test.
TASK-002 | 1.2 | Scope, assumptions and non-goals | Record MVP boundary, unresolved business rules and explicit exclusions. | Design | 0.5 | Must | Not Started | TASK-001 | Scope is implementable within 28 hours and no assumption is hidden.
TASK-003 | 1.3 | Invariants and failure modes | Define ownership, qualification, overlap, atomicity, retry and timezone rules. | Design | 0.75 | Must | Not Started | TASK-002 | Invariants and expected failures are listed with handling decisions.
TASK-004 | 1.4 | Architecture and components | Choose modular monolith/layered design and describe every component responsibility. | Design | 0.75 | Must | Not Started | TASK-002 | Architecture diagram and component table match intended code.
TASK-005 | 1.5 | ERD and database decisions | Design entities, keys, status, indexes and idempotency storage. | Design | 0.75 | Must | Not Started | TASK-003 | ERD supports all acceptance criteria and availability queries.
TASK-006 | 1.6 | Initial API contract | Define endpoints, payloads, status codes and common response format. | Design | 0.5 | Must | Not Started | TASK-003 | Request/response examples cover success and major failures.
TASK-007 | 1.7 | GenAI design decision log | Record AI proposal, human decision and verification method. | Documentation | 0.25 | Should | Not Started | TASK-001 | At least three meaningful design decisions are traceable.
TASK-008 | 2.1 | Laravel 11 project setup | Initialize PHP 8.3 application, configuration and test environment. | Setup | 0.75 | Must | Not Started | TASK-006 | artisan about and empty test suite run successfully.
TASK-009 | 2.2 | Docker Compose environment | Configure app and PostgreSQL services with health checks. | Setup | 0.75 | Should | Not Started | TASK-008 | Fresh Docker startup reaches healthy state.
TASK-010 | 2.3 | Migrations, constraints and indexes | Create all tables, foreign keys, unique constraints and booking indexes. | Setup | 1 | Must | Not Started | TASK-005,TASK-008 | migrate:fresh succeeds and constraints reject invalid references.
TASK-011 | 2.4 | Models and relationships | Implement typed casts and Eloquent associations. | Setup | 0.75 | Must | Not Started | TASK-010 | Relationships load correctly and status/time casts are explicit.
TASK-012 | 2.5 | Factories and seeders | Provide deterministic demo and test data. | Setup | 0.75 | Must | Not Started | TASK-011 | migrate:fresh --seed produces a cURL-ready scenario.
TASK-013 | 3.1 | TimeRange value object | Implement interval validation, duration calculation and overlap semantics. | Core | 0.75 | Must | Not Started | TASK-012 | Pure unit tests cover valid, invalid and boundary intervals.
TASK-014 | 3.2 | Qualified technician query | Find active, skilled, correct-dealership technicians without overlaps. | Core | 1 | Must | Not Started | TASK-013 | Wrong dealership, skill and overlap cases are excluded.
TASK-015 | 3.3 | Available service bay query | Find active, correct-dealership bays without overlaps. | Core | 0.75 | Must | Not Started | TASK-013 | Busy and wrong-dealership bays are excluded.
TASK-016 | 3.4 | CheckAvailability action | Calculate full period and combine resource availability results. | Core | 1 | Must | Not Started | TASK-014,TASK-015 | Returns deterministic result without reserving resources.
TASK-017 | 3.5 | Availability endpoint | Validate input and expose advisory availability response. | Core | 0.5 | Must | Not Started | TASK-016 | Endpoint returns 200 and documented response shape.
TASK-018 | 4.1 | Store request and DTO | Define validated request and immutable use-case input. | Core | 0.5 | Must | Not Started | TASK-017 | Action receives no HTTP Request dependency.
TASK-019 | 4.2 | Transactional CreateAppointment | Verify ownership, allocate both resources and persist atomically. | Core | 1.25 | Must | Not Started | TASK-018 | Successful booking returns 201 and stores all associations.
TASK-020 | 4.3 | Concurrency locking strategy | Lock resources in deterministic order and recheck overlaps inside transaction. | Reliability | 1 | Must | Not Started | TASK-019 | Competing requests cannot both reserve the same resource.
TASK-021 | 4.4 | Common API response and exception mapping | Implement ApiResponse, ErrorCode, DomainException and global rendering. | Core | 0.5 | Must | Not Started | TASK-019 | 409/422/404/500 responses use one stable envelope.
TASK-022 | 4.5 | Appointment detail endpoint | Return persisted appointment through an API Resource. | Core | 0.75 | Should | Not Started | TASK-021 | GET returns documented associations and timestamps.
TASK-023 | 5.1 | Idempotency-Key support | Persist key, request hash and replayable result for POST retries. | Reliability | 1.5 | Should | Not Started | TASK-020 | Same key/payload does not create another row; changed payload returns 409.
TASK-024 | 5.2 | Dealership business-hours rule | Validate complete local appointment period against opening hours. | Reliability | 0.75 | Should | Not Started | TASK-019 | Outside-hours appointment is rejected with a stable code.
TASK-025 | 5.3 | Request ID middleware | Create/propagate X-Request-ID and add it to log context and response. | Observability | 0.5 | Should | Not Started | TASK-021 | One request ID correlates response and all server logs.
TASK-026 | 5.4 | Structured event logging | Log requested, confirmed and rejected events without unnecessary PII. | Observability | 0.5 | Should | Not Started | TASK-025 | Logs contain event, request_id, IDs, latency and safe reason.
TASK-027 | 5.5 | Metrics and tracing design | Document counters, latency metrics and OpenTelemetry evolution. | Observability | 0.25 | Could | Not Started | TASK-026 | System Design accurately distinguishes implemented vs future signals.
TASK-028 | 5.6 | Cancellation endpoint | Optionally change confirmed to cancelled and release resources. | Core | 0.5 | Could | Not Started | TASK-023 | Cancelled appointments no longer block availability.
TASK-029 | 6.1 | Availability feature tests | Test resource pair availability and rejection cases. | Testing | 0.75 | Must | Not Started | TASK-017 | Core availability branches have database-backed tests.
TASK-030 | 6.2 | Appointment feature tests | Test success, ownership, resource conflicts, rollback and boundaries. | Testing | 1 | Must | Not Started | TASK-021 | Acceptance criteria have response and database assertions.
TASK-031 | 6.3 | Idempotency tests | Test replay and key/payload conflict. | Testing | 0.5 | Should | Not Started | TASK-023 | Duplicate retry behavior is deterministic.
TASK-032 | 6.4 | Concurrency verification | Run or document a reproducible competing-request integration test. | Testing | 0.75 | Must | Not Started | TASK-020 | Evidence supports the concurrency-safety claim; limitations are explicit.
TASK-033 | 6.5 | OpenAPI and cURL harness | Document executable happy and failure flows. | Documentation | 0.5 | Must | Not Started | TASK-021 | Reviewer can test without a frontend.
TASK-034 | 6.6 | CI workflow | Run dependency validation, formatting and tests with PostgreSQL. | Setup | 0.5 | Should | Not Started | TASK-030 | Pipeline is green on a clean checkout.
TASK-035 | 7.1 | Finalize System Design | Synchronize diagrams, flows, decisions and limitations with code. | Documentation | 1 | Must | Not Started | TASK-032,TASK-034 | All requested design sections are present and truthful.
TASK-036 | 7.2 | Complete README | Provide build, run, test, cURL and troubleshooting instructions. | Documentation | 0.75 | Must | Not Started | TASK-033 | A new reviewer can run the application from README alone.
TASK-037 | 7.3 | AI Collaboration Narrative | Describe guidance, verification, refinement and ownership with examples. | Documentation | 0.5 | Must | Not Started | TASK-035 | Narrative includes concrete AI proposal and human verification examples.
TASK-038 | 7.4 | Fresh-install verification | Rebuild database, seed, test and run cURL from a clean environment. | Submission | 0.5 | Must | Not Started | TASK-036 | No uncommitted dependency or undocumented step is required.
TASK-039 | 7.5 | Video script | Prepare an 8-minute structure aligned with evaluation dimensions. | Submission | 0.5 | Must | Not Started | TASK-035,TASK-037 | Script covers intro, design, implementation, AI, demo and learning.
TASK-040 | 7.6 | Record and review video | Record 5-10 minute presentation and verify audio/demo readability. | Submission | 0.75 | Must | Not Started | TASK-038,TASK-039 | Final video is within time and all demo steps succeed.

## 7-Day Plan
Day | Focus | Tasks | Hours | Exit Criterion
1 | Requirements & System Design | TASK-001 to TASK-007 | 4 | Requirement baseline and architecture
2 | Setup & Persistence | TASK-008 to TASK-012 | 4 | Running seeded Laravel/PostgreSQL environment
3 | Availability Core | TASK-013 to TASK-017 | 4 | Availability endpoint
4 | Appointment & Concurrency | TASK-018 to TASK-022 | 4 | Atomic booking and common errors
5 | Reliability & Observability | TASK-023 to TASK-028 | 4 | Idempotency, hours and logs
6 | Testing, API Contract & CI | TASK-029 to TASK-034 | 4 | Green suite and OpenAPI/cURL
7 | Documentation & Submission | TASK-035 to TASK-040 | 4 | Final docs, video and clean verification

## Req Traceability
Req ID | Requirement | Design / Component | Tasks | Verification | Status
AC-01 | Request appointment for vehicle, service type, dealership and desired time | POST /api/v1/appointments | TASK-018,TASK-019,TASK-030 | Feature: successful booking | Planned
AC-02 | Check qualified technician and service bay for full duration | TimeRange and availability queries | TASK-013 to TASK-017,TASK-020,TASK-029,TASK-032 | Unit + feature + concurrency | Planned
AC-03 | Persist appointment with customer, vehicle, technician and bay | appointments table and resource | TASK-010,TASK-019,TASK-022,TASK-030 | Database and response assertions | Planned
BF-01 | Scalability and performance | Indexes, bounded queries, modular monolith | TASK-005,TASK-010,TASK-035 | Design review/query plan | Planned
BF-02 | Reliability | Transaction, locking, idempotency | TASK-020,TASK-023,TASK-032 | Integration evidence | Planned
BF-03 | Maintainability | Action/Query/DTO/Value Object structure | TASK-004,TASK-035 | Code review | Planned
BF-04 | Observability | Request ID, logging, metric plan | TASK-025 to TASK-027 | Log assertions/design review | Planned

## Test Matrix
Test ID | Scenario | Level | Rule / Requirement | Task | Priority | Status
UT-01 | TimeRange rejects end <= start | Unit | INV-07 | TASK-013 | Must | Not Started
UT-02 | Overlap: partial left/right | Unit | INV-05/06 | TASK-013 | Must | Not Started
UT-03 | Back-to-back ranges do not overlap | Unit | AS-04 | TASK-013 | Must | Not Started
FT-01 | Booking succeeds with both resources | Feature | AC-01/02/03 | TASK-030 | Must | Not Started
FT-02 | All qualified technicians busy | Feature | INV-05 | TASK-029 | Must | Not Started
FT-03 | All bays busy | Feature | INV-06 | TASK-029 | Must | Not Started
FT-04 | Technician lacks requested skill | Feature | INV-03 | TASK-029 | Must | Not Started
FT-05 | Resources belong to another dealership | Feature | INV-02 | TASK-029 | Must | Not Started
FT-06 | Vehicle belongs to another customer | Feature | INV-01 | TASK-030 | Must | Not Started
FT-07 | Failed allocation rolls back | Feature | INV-08/09 | TASK-030 | Must | Not Started
IT-01 | Same idempotency key and payload replays result | Integration | INV-10 | TASK-031 | Should | Not Started
IT-02 | Same key with different payload returns 409 | Integration | INV-10 | TASK-031 | Should | Not Started
IT-03 | Competing requests cannot double-book | Integration | INV-05/06 | TASK-032 | Must | Not Started

## Lists
Status | Priority | Category
Not Started | Must | Design
In Progress | Should | Setup
Blocked | Could | Core
Done |  | Reliability
Observability
Testing
Documentation
Submission